## backlog
Backlog
Add your board's description here
Sprint 1
Name | Person | Status | Graded Criteria | Checkbox | Due Date | Item ID (auto generated)
Dockerfile for project set-up and works |  | Working on it |  |  | 2023-02-10 | 1149721040
Correct branches for GitFlow workflow created - includes `master`, `develop`, and `release` branches |  | Working on it |  |  | 2023-02-10 | 1149723301
First release created on GitHub |  | Working on it |  |  | 2023-02-10 | 1149723305
Code of Conduct defined | nouha | Working on it |  |  | 2023-02-10 | 1149724333
GitHub project for coursework set-up |  | Working on it | Code quality including comments |  | 2023-02-10 | 1149721036
Product Backlog created | nouha | Done | Metrics from GitHub. Also used to assess individual contribution |  | 2023-02-10 | 1149721038
|  |  |  | 0/6 | 2023-02-10
Sprint 2
Name | Person | Status | Graded Criteria | Checkbox | Due Date | Item ID (auto generated)
Full use cases defined |  | Working on it |  |  | 2023-03-10 | 1149729100
Use case diagram created |  | Working on it | Metrics from GitHub. Also used to assess individual contribution |  | 2023-03-10 | 1149729193
Tasks defined as user stories |  | Working on it | Code quality including comments |  | 2023-03-10 | 1149726183
Sprint Boards being used |  | Working on it | Correct usage of branches |  | 2023-03-10 | 1149729066
Project integrated with Zube.io |  | Working on it | Continuous integration working |  | 2023-03-10 | 1149726845
Kanban/Project Board being used |  | Working on it | Use cases well defined |  | 2023-03-10 | 1149728134
Issues being used on GitHub |  | Working on it | Project requirements met |  | 2023-03-10 | 1149726138
|  |  |  | 0/7 | 2023-03-10
Sprint 3
Name | Person | Status | Graded Criteria | Checkbox | Due Date | Item ID (auto generated)
Use case diagram created |  | Working on it | Metrics from GitHub. Also used to assess individual contribution |  | 2023-03-31 | 1149729909
Updated task board of user stories showing progress in the technical deliverables |  | Working on it | Code quality including comments |  | 2023-03-31 | 1149730218
Tests running on Travis CI |  | Working on it | Correct usage of branches |  | 2023-03-31 | 1149730075
Suitable integration tests defined |  | Working on it | Continuous integration working |  | 2023-03-31 | 1149730047
Implementation progress towards final version of application: |  | Working on it | Kanban/Project Board being used |  | 2023-03-31 | 1149730438
Github repository showing work from all members of the team |  | Working on it | Quality and coverage of unit tests |  | 2023-03-31 | 1149730348
. |  |  | Project requirements met |  | 2023-03-31 | 1149769933
|  |  |  | 0/7 | 2023-03-31
Spint 4
Name | Person | Status | Graded Criteria | Checkbox | Due Date | Item ID (auto generated)
A group report (maximum 10 pages), where you need to present your work as a team |  | Working on it |  |  | 2023-03-28 | 1149731971
Overall application quality and success at meeting the aims set out during the design process |  | Working on it | Metrics from GitHub. Also used to assess individual contribution |  | 2023-04-28 | 1149731205
Metrics from GitHub: used to assess individual contribution |  | Working on it | Code quality including comments |  | 2023-04-28 | 1149731635
Final version of the task board and project requirements met |  | Working on it | Correct usage of branches |  | 2023-03-28 | 1149731776
Deployment working |  | Working on it | Continuous integration working |  | 2023-03-28 | 1149731845
Bug reporting system set-up |  | Working on it | Kanban/Project Board being used |  | 2023-03-28 | 1149731912
Application deployable using a docker-compose file, data can be provided separately |  | Working on it | Quality and coverage of unit tests |  | 2023-03-28 | 1149731734
|  |  |  | 0/7 | 2023-03-28 to 2023-04-28

## backlog-updates
Backlog | Updates
Item ID | Item Name | Content Type | Content Type | User | Created At | Update Content | Likes Count | Asset IDs | Post ID | Parent Post ID
1149730438 | Implementation progress towards final version of application: | Update |  | nouha | 03/February/2023 11:25:43 AM | o Database design o Databaseimplementationwithpre-filleddata o HTMLpagesavailablegeneratedfromPUG,perhapswithsomestatic content o At least some dynamic content being pulled from your database to your templates via Pug - concentrate on views of your data | 0 |  | 24435468